## 1_Cover
INDIE FILM FINANCE PLAN
$2,000,000 Production Budget ¦ $1,040,000 Equity Raise ¦ Single-Film LLC ¦ [PROJECT TITLE]
PROJECT SNAPSHOT — Edit yellow/blue cells to customize
Film Title | [PROJECT TITLE]
Genre | [e.g. Thriller / Drama / Horror]
Director | [DIRECTOR NAME]
Producer | [PRODUCER NAME]
Key Cast | [LEAD ACTOR / TBD]
Sales Agent | [TBD]
Shoot State | [STATE — drives tax credit %]
Schedule | 30-Day Principal Photography, Digital 4K
Festival Target | Sundance / SXSW / Tribeca
Production Start | Q3 2026
Delivery | Q1 2027
Rating | R / PG-13
FINANCING SUMMARY (Auto-calculates from Assumptions)
Total Budget
Equity Being Raised
Tax Credit (Rebate)
Senior Debt
Gap / Mezz
Min. Investment / Investor
Recoupment Premium
Investor Backend
Raise Close
Legal Vehicle
SHEET NAVIGATOR
2_Assumptions | Master inputs — start here to customize for your project
3_Budget | Full production budget by department: ATL, BTL, Post, G&A, contingency
4_Capital_Stack | All financing sources, risk positions, and investor terms at a glance
5_Waterfall | Revenue waterfall — complete investor return calculator
6_Revenue_Model | Distribution window revenue: Conservative / Base / Upside scenarios
7_Cash_Flow | Monthly cash flow: capital deployment and distribution proceeds timeline
8_Sensitivity | ROI / MOIC / IRR sensitivity matrices
9_Risk_Register | Risk factors, probability, impact, and mitigation strategies
COLOR LEGEND
Blue = Input | Change to customize
Black = Formula | Do not edit
Green = Cross-Sheet Link | Pulls from another tab
Yellow Background | Key assumption to review
Disclaimer: Illustrative examples only. Not an offer of securities. Consult entertainment attorneys before raising capital. Generated: March 2026

## 2_Assumptions
MASTER ASSUMPTIONS — Change blue cells; all other sheets update automatically
Assumption | Value | Notes | Benchmark
A. PROJECT & BUDGET
Project Title | [PROJECT TITLE] | Your film title as it appears in legal docs | —
Genre | [e.g. Thriller] | Drives comparable film selection | —
Total Production Budget ($) | 2000000 | All-in: ATL + BTL + Post + G&A + Bond + Contingency | $500K–$10M
State Tax Credit / Rebate ($) | 400000 | ~20-35% qualifying in-state spend; received post-wrap | 20-45% of budget
Senior Debt – Tax Credit Loan ($) | 360000 | 90% advance on tax credit; first-position lien on credit proceeds | 90% × credit
Gap / Mezz Financing ($) | 0 | Second-position; use only if needed to close gap; avoid at $750K | 0-15% of budget
Pre-Sale Loan ($) | 0 | Against executed MG contracts; viable at $2M+ with sales agent | 0-20% at $2M+
TOTAL EQUITY RAISE ($) |  | Budget minus all debt/soft money = equity needed from investors | Auto
Est. # of Investors | 10 | Divide equity / min. investment for rough count | 5-30 typical
Min. Investment Per Investor ($) | 50000 | Reg D 506(b) accredited investor minimum | $25K-$100K
B. INVESTOR TERMS & WATERFALL
Investor Recoupment Premium (%) | 20% | % above principal before backend; typ. 15-25% | 15%-25%
Backend Split — Investor Pool (%) | 50% | % of net profit after hurdle; other 50% to producer | 40%-50%
Backend Split — Producer (%) |  | Auto-calculated from investor split | Auto
Senior Debt Interest Rate | 9% | Tax credit bridge; 8-12% typical | 8%-12%
Gap Loan Interest Rate | 16% | Higher risk; 12-20% for gap lenders | 12%-20%
Loan Term (months) | 18 | Bridge to distribution receipt; affects IRR | 12-36 months
C. DISTRIBUTION ASSUMPTIONS (used in Waterfall & Revenue Model)
Distribution Strategy | Limited Theatrical + SVOD | Drives P&A and distributor fee structure | —
Exhibitor / Theater Split (%) | 50% | Theaters retain ~50-55% of theatrical gross | 45%-55%
P&A / Marketing Budget ($) | 150000 | Recouped before any commissions | $50K-$2M+
Distribution Fee (%) | 30% | % of net film rental; negotiable | 25%-35%
Sales Agent Commission (%) | 12% | % of gross foreign receipts | 10%-15%
CAMA (Collection Account)? | Yes | Strongly recommended — protects waterfall order | Yes (best practice)
Completion Bond Required? | Yes | Required by most gap/debt providers; ~2-3% in budget | Yes if debt used
D. LEGAL, OFFERING & TIMELINE
Raise Close Target | Q2 2026 | Investment deadline for pitch materials | —
Legal Vehicle | Single-Purpose LLC | Investors = Class A Limited Members; filmmaker = Manager | LLC (SPE)
Securities Exemption | Reg D / Rule 506(b) | Accredited investors only; no general solicitation (or 506(c) w/ verification) | Reg D
PPM Required? | Yes — Attorney Drafted | Legally binding; must be completed before accepting any funds | Always
SAG-AFTRA Tier | Modified Low Budget | Confirm eligibility; drives all cast minimum rates | Budget-dependent
E&O Insurance ($) | 1000000 | Required by all major distributors at delivery | $1M minimum

## 3_Budget
PRODUCTION BUDGET — Top Sheet by Department ¦ $2M Example ¦ Blue = input, Black = formula
Line Item | Budget ($) | % Total | Prior Est. ($) | Variance ($) | Notes
ABOVE THE LINE
Story & Rights / Option | 40000 |  | 40000 |  | Option on underlying IP rights
Screenplay / Final Polish | 25000 |  | 25000 |  | WGA minimum or negotiated fee
Producer(s) Fee | 60000 |  | 60000 |  | Lead producer; deferral common
Director Fee | 100000 |  | 100000 |  | DGA or non-union negotiated
Lead Cast | 200000 |  | 200000 |  | SAG Modified Low Budget rates
Supporting Cast | 50000 |  | 50000 |  | Supporting & day players
ATL SUBTOTAL
BELOW THE LINE — PRODUCTION
1st AD / Production Staff | 35000 |  | 35000 |  | Dept coordinators + PAs
Camera (crew + equipment) | 80000 |  | 80000 |  | DP + camera package + lenses
Grip & Electric | 120000 |  | 120000 |  | Gaffer, key grip, truck + equip.
Art Dept / Production Design | 90000 |  | 90000 |  | PD, set dec, props, builds
Wardrobe / Costume | 35000 |  | 35000 |  | Costumes, rentals, laundry
Hair & Makeup | 28000 |  | 28000 |  | Key MUA + hair dept
Sound (Production) | 22000 |  | 22000 |  | Mixer, boom, kit rental
Locations & Permits | 65000 |  | 65000 |  | Location fees, scouts, permits
Transportation | 55000 |  | 55000 |  | Trucks, base camp, talent
Catering & Craft Services | 40000 |  | 40000 |  | On-set food ~30 days
Extras / Background | 18000 |  | 18000 |  | Featured + general BG
Stunts | 15000 |  | 15000 |  | Stunt coordinator + personnel
BTL PRODUCTION SUBTOTAL
POST-PRODUCTION
Editorial (editor + asst.) | 75000 |  | 75000 |  | ~12-week edit; gear/software
Color Grading / DI | 40000 |  | 40000 |  | Color correction + finishing
Music Score + Licensing | 35000 |  | 35000 |  | Composer fee + sync budget
Sound Design / Mix | 30000 |  | 30000 |  | Sound supervisor + mix sessions
VFX / Title Graphics | 20000 |  | 20000 |  | Basic VFX; title design
Deliverables (DCP, IMF, etc.) | 20000 |  | 20000 |  | DCP master + digital deliverables
Closed Captions / Subtitles | 5000 |  | 5000 |  | Required by all streaming platforms
POST SUBTOTAL
GENERAL & ADMINISTRATIVE
Production + E&O Insurance | 37000 |  | 37000 |  | Cast, equip., GL, workers comp + E&O
Completion Bond (~2.5%) | 50000 |  | 50000 |  | Required by gap/debt lenders; ~2-3% total
Legal (entertainment attorney) | 20000 |  | 20000 |  | PPM, LLC formation, all contracts
Accounting / Production Audit | 15000 |  | 15000 |  | Production accountant + year-end CPA
Festival Submissions & Fees | 10000 |  | 10000 |  | Entry fees, screeners, travel
Marketing / PR Seed | 20000 |  | 20000 |  | Key art, trailer, website, social
G&A SUBTOTAL
CONTINGENCY (10% of BTL + Post) |  |  |  |  | Standard 10% overage reserve
TOTAL PRODUCTION BUDGET
Illustrative figures. Costs vary by union status, genre, location, schedule. Completion bond ~2.5% in G&A. Contingency = 10% of BTL+Post.
ATL
BTL Prod
Post
G&A
Contingency

## 4_Capital_Stack
CAPITAL STACK — Financing Sources, Risk Position & Investor Terms
Financing Layer | Amount ($) | % of Budget | Position | Target Return | Notes
NON-DILUTIVE / SOFT MONEY (Received First)
State Tax Credit / Production Rebate |  |  | Non-dilutive | N/A | Received post-wrap; used to repay tax credit loan
Federal / Intl Co-Pro Incentive | 0 |  | Non-dilutive | N/A | Only if co-production treaty applies
Film Fund / Grant | 0 |  | Non-dilutive | N/A | Sundance, IFC, regional arts councils, etc.
SOFT MONEY SUBTOTAL
SENIOR DEBT — FIRST POSITION
Tax Credit Bridge Loan (90% advance) |  |  | 1st Position |  | Secured on tax credit; repaid upon receipt
Intl Pre-Sale Loan (90% of MGs) | 0 |  | 1st Position | 8-12% | Secured against MG contracts; requires sales agent
Domestic MG / Output Deal | 0 |  | 1st Position | 8-12% | Domestic advance; uncommon at <$2M
SENIOR DEBT SUBTOTAL
GAP / MEZZANINE — SECOND POSITION
Gap Loan (against unsold territories) |  |  | 2nd Position |  | Lender holds security in unsold territory rights
Mezzanine / Subordinated Note | 0 |  | 2nd Position | 15-20% | Subordinated to senior debt; pari passu or junior to gap
GAP / MEZZ SUBTOTAL
EQUITY — THIRD POSITION (At-Risk Capital)
Equity Investor Pool (Class A Members) |  |  | 3rd Position | 120% Hurdle + 50% Backend | See Waterfall sheet for full return mechanics
Producer Deferred / Equity (Class B) | 0 |  | 3rd Position | Backend only | Deferred fee converted to equity at close
EQUITY SUBTOTAL
TOTAL FINANCING |  |  |  |  | Must equal Total Production Budget on Assumptions sheet
INVESTOR TERMS AT A GLANCE
Investment Vehicle
Total Equity Raising
Min. Investment
Investor Class | Class A Limited Members
Recoupment Priority | First from Net Producer Proceeds
Recoupment Premium
Backend — Investors
Backend — Producer
Raise Close Target
Legal Exemption

## 5_Waterfall
REVENUE WATERFALL & INVESTOR RETURN CALCULATOR ¦ Change C4 to run scenarios
GROSS REVENUE INPUT — Linked from Revenue Model Base Case; override here to run scenarios
Total Gross Revenue — All Windows, All Years | 3500000 | Scenario revenue input — change to model different outcomes
Waterfall Step | Amount ($) | Running Balance ($) | Explanation
① Gross Revenue (All Windows) |  |  | Total revenue across all distribution windows and years
② Less: Exhibitor / Theater Take |  |  | Theaters retain ~50% of theatrical gross
③ Film Rental (Net of Exhibitor) |  |  | Revenue after theater split; enters distribution
④ Less: P&A / Distribution Costs |  |  | Distributor recoups prints, advertising, and marketing first
⑤ Less: Distribution Fee |  |  | Fee on net film rental (after P&A); per distribution deal
⑥ Less: Sales Agent Commission |  |  | Sales agent commission on gross foreign receipts
⑦ NET PRODUCER PROCEEDS |  |  | Revenue reaching Production LLC — enters investor waterfall
⑧ Less: Senior Debt Repayment |  |  | Tax credit loan principal + accrued interest
⑨ Less: Gap / Mezz Repayment |  |  | Gap loan principal + interest; 0 if no gap financing used
⑩ AVAILABLE FOR EQUITY RECOUPMENT |  |  | Remaining after all debt fully serviced
⑪ Investor Recoupment (Principal + Premium) |  |  | Investors recover principal × (1 + premium); capped at available
⑫ REMAINING FOR PROFIT SPLIT |  |  | Backend pool — flows only if recoupment fully achieved
⑬ Investor Backend |  |  | Investor pool's backend share of remaining proceeds
⑭ Producer / Filmmaker Backend |  |  | Producer's share; distributed to talent and creative team
INVESTOR RETURN SUMMARY
Equity Invested |  | Change C4 above to model different revenue scenarios
Investor Recoupment (incl. premium)
Investor Backend
TOTAL INVESTOR RETURN ($)
Net Profit to Investor ($)
Return Multiple (MOIC)
Simple Cash-on-Cash ROI
Producer Net Proceeds
Breakeven Gross Revenue
NOTE: Simple ROI does not account for time value of money. IRR will be materially lower over 18-36 month hold periods. Waterfall assumes full recoupment before backend flows; if recoupment not achieved, investors receive available balance only.

## 6_Revenue_Model
REVENUE MODEL — Distribution Windows ¦ Conservative / Base / Upside Scenarios
Revenue Stream / Window | Conservative ($) | Base ($) | Upside ($) | Key Assumptions & Drivers
THEATRICAL — DOMESTIC
Gross Box Office | 800000 | 1800000 | 5000000 | Platform/limited release. Wide = much higher P&A ($1M+). Rare for $2M budget films.
Less: Exhibitor Take (50%) |  |  |  | Calculated from Assumptions (C25); ~50-55% to theaters
Less: P&A / Marketing Recoupment |  |  |  | From Assumptions C26; recouped off the top before fees
Less: Distribution Fee |  |  |  | On net film rental after P&A; from Assumptions C27
Domestic Theatrical NET |  |  |  | Net proceeds flowing to LLC from theatrical
INTERNATIONAL SALES
International MGs (pre-sold) | 50000 | 150000 | 500000 | Minimum guarantees from intl distributors via sales agent
Foreign Sales Overages | 0 | 50000 | 200000 | Overage above MG; only when film overperforms in territory
Less: Sales Agent Commission |  |  |  | From Assumptions C28; ~12% of gross intl receipts
International NET |  |  |  | Net international proceeds to LLC
STREAMING — SVOD
SVOD License Fee (Netflix / Prime / MUBI) | 75000 | 300000 | 1500000 | Festival acquisition flat fee. Softening 2025-26 market. Star-driven premium.
STREAMING — TVOD (Transactional)
TVOD Rental/Purchase (Apple, Amazon, Vudu) | 6000 | 25000 | 90000 | Avg indie ~$4-8K; breakout genre hits can reach $50-100K.
STREAMING — AVOD / FAST
AVOD / FAST Revenue (Tubi, Pluto, Roku) | 4000 | 15000 | 55000 | Ad-share revenue; low per-title but recurring library value
TELEVISION
Domestic TV (Cable / PBS / Premium) | 20000 | 75000 | 300000 | Depends heavily on genre; premium cable for drama/thriller
International TV (via sales agent) | 10000 | 50000 | 200000 | Territory-by-territory license fees; managed via sales agent
ANCILLARY
Educational / Non-Theatrical | 5000 | 15000 | 50000 | Universities, libraries, airlines; modest but recurring
Soundtrack / Merchandise | 0 | 5000 | 25000 | Only material for music-driven or franchise-adjacent titles
TAX INCENTIVE
State Tax Credit / Production Rebate |  |  |  | From Assumptions sheet; same across all scenarios
TOTAL GROSS REVENUE — ALL WINDOWS |  |  |  | Sum of all distribution windows + tax credit
Conservative
Base
Upside

## 7_Cash_Flow
MONTHLY CASH FLOW — Investment through Production to Distribution Proceeds
← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── →
Cash Flow Category | Mo 1 | Mo 2 | Mo 3 | Mo 4 | Mo 5 | Mo 6 | Mo 7 | Mo 8 | Mo 9 | Mo 10 | Mo 11 | Mo 12 | Mo 18 | Mo 24+
CAPITAL INFLOWS
Equity Investment Draws | ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 1: 1040000
Tax Credit Bridge Loan | ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 1: 360000
Gap / Mezz Loan (if used)
TOTAL INFLOWS
PRODUCTION EXPENDITURES
Pre-Production (dev, prep, legal) | ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 1: 80000; ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 2: 120000
Principal Photography | ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 3: 300000; ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 4: 300000; ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 5: 200000
Post-Production | ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 5: 50000; ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 6: 200000; ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 7: 200000; ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 8: 150000
General & Administrative (monthly) | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 5000 | 5000
Completion Bond & Insurance (upfront) | ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 1: 87000
TOTAL EXPENDITURES
DISTRIBUTION PROCEEDS
SVOD / Streaming License Fee | ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 10: 300000
International MGs (on delivery) | ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 9: 150000
Theatrical Net Proceeds | ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 10: 100000; ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 11: 200000; ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 12: 100000
State Tax Credit Receipt | ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 9: 400000
TVOD / AVOD / TV (ongoing) | ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 11: 10000; ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 12: 15000; ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 18: 20000; ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 24+: 30000
TOTAL PROCEEDS
DEBT REPAYMENT
Tax Credit Bridge Loan Repayment | ← Pre-Production ────── Production ───────── Post-Production ────────────── Distribution ────────────────────── → Mo 9: -392400
Gap Loan Repayment
TOTAL REPAYMENTS
NET CASH POSITION
CUMULATIVE CASH
Note: Illustrative cash flow only. Actual deployment will vary based on production schedule, distribution deal timing, and loan draw terms. Negative values in expenditures = cash out; positive in proceeds = cash in.

## 8_Sensitivity
SENSITIVITY ANALYSIS — ROI, MOIC & Breakeven by Revenue Scenario
TABLE 1 — Simple Cash-on-Cash ROI by Gross Revenue Scenario (Base Distribution)
Equity Invested ↓ / Gross Revenue → | $500K | $1M | $1.5M | $2.5M | $3.5M | $5M
$600,000 equity | -100% | -100% | -73.4% | -0.4% | 46.3% | 101%
$800,000 equity | -100% | -100% | -80.05% | -25.3% | 24.73% | 65.79%
$1,040,000 equity | -100% | -100% | -84.65% | -42.54% | -0.4231% | 41.38%
$1,200,000 equity | -100% | -100% | -86.7% | -50.2% | -13.7% | 30.53%
$1,500,000 equity | -100% | -100% | -89.36% | -60.16% | -30.96% | 12.84%
TABLE 2 — Investor MOIC by Gross Revenue & Recoupment Premium ($1.04M equity base)
Recoup Premium ↓ / Revenue → | $500K | $1M | $1.5M | $2.5M | $3.5M | $5M
10% premium | 0 | 0 | 0.15346 | 0.57462 | 0.99577 | 1.3638
15% premium | 0 | 0 | 0.15346 | 0.57462 | 0.99577 | 1.3887
20% premium | 0 | 0 | 0.15346 | 0.57462 | 0.99577 | 1.4138
25% premium | 0 | 0 | 0.15346 | 0.57462 | 0.99577 | 1.4387
30% premium | 0 | 0 | 0.15346 | 0.57462 | 0.99577 | 1.4638
TABLE 3 — Estimated Breakeven Gross Revenue Required by Distribution Strategy
Distribution Strategy | Exhibitor % | Distrib. Fee | P&A ($) | SA Comm. | Equity | Breakeven Gross
SVOD-First (No Theatrical) | 0% | 25% | 0 | 10% | 1040000 | 2524000
Limited Theatrical + SVOD | 50% | 30% | 150000 | 12% | 1040000 | 7784000
Full Theatrical Wide Release | 52% | 35% | 1000000 | 12% | 1040000 | 13752000
International Pre-Sales Only | 0% | 20% | 50000 | 12% | 1040000 | 2486000
Hybrid (Self-Distributed) | 10% | 15% | 75000 | 5% | 1040000 | 2399000
Note: ROI, MOIC, and breakeven figures are illustrative calculations using simplified assumptions. Actual returns depend on negotiated deal terms, collection account mechanics, hold period, and distribution performance.

## 9_Risk_Register
RISK REGISTER — Investor-Facing Risk Factors & Mitigation Strategies
Risk Factor | Category | Probability | Impact (1-5) | Risk Score | Mitigation | Residual Risk / Status
Completion Risk — Production over budget or fails to complete | Production | 25% | 4 | 1 | Completion bond from recognized provider; 10% contingency in budget; experienced producer | Reduced via bond; monitor weekly burn rate
No Distribution — Film not acquired or finds no distribution deal | Commercial | 40% | 5 | 2 | Attach sales agent pre-production; target A-list festivals; compare to comps with distribution | Build SVOD-first strategy as fallback
Revenue Underperformance — Distribution proceeds insufficient to recoup | Financial | 45% | 5 | 2.2 | Conservative waterfall projections; recoupment priority before any backend; diversified revenue windows | Investors receive pro-rata of available; full loss possible
SVOD Market Contraction — Platform licensing fees decline further | Market | 35% | 4 | 1.4 | Develop multi-window strategy; do not rely solely on one platform; build TVOD + AVOD as base | Multiple fallback windows modeled
Key Person Risk — Director, star, or producer leaves project | Production | 15% | 5 | 0.8 | Cast and key person insurance; attached talent clauses in agreements; backup casting plan | Completion bond may cover; disruption risk remains
Tax Credit Risk — Rebate denied, delayed, or reduced | Financial | 20% | 4 | 0.8 | Work with qualified production tax attorney; obtain pre-approval letter if available; conservative credit estimate | Do not deploy until credit is confirmed
Legal / Chain of Title Issues | Legal | 10% | 5 | 0.5 | Full chain of title clearance before close; E&O insurance; copyright registration; music clearance | E&O policy transfers risk at delivery
Interest Rate / Bridge Loan Risk — Costs exceed projection | Financial | 15% | 3 | 0.4 | Fixed-rate bridge agreement where possible; model sensitivity on Sensitivity sheet | Modeled at 9% senior; 16% gap
Investor Relations Risk — Investor default or early withdrawal | Operational | 10% | 4 | 0.4 | Binding subscription agreements with LLC; PPM disclaims redemption rights; clear closing conditions | No investor withdrawal after subscription signed
Festival Rejection — Film fails to secure marquee premiere | Commercial | 40% | 3 | 1.2 | Direct distribution plan (SVOD-first) as backup; trailer-driven digital release strategy | Box office/SVOD unaffected by festival absent buzz boost
Copyright / Music Clearance Risk | Legal | 20% | 3 | 0.6 | Pre-clear all music before post; use original score; budget for festival print clearances | E&O insurance and music supervisor on board
Currency / Foreign Exchange Risk | Financial | 25% | 3 | 0.8 | Invoice intl pre-sales in USD; use collection account in USD; minimize EUR/GBP exposure | Currency hedging costly at indie budget; accept residual risk
Reputational / Talent Controversy | Reputational | 10% | 4 | 0.4 | Morality clauses in all talent agreements; crisis PR plan; insurance | Insurance may cover; distribution impact unpredictable
Technology / Data Loss Risk | Operational | 10% | 3 | 0.3 | Daily cloud backup of all media and data (RAID + offsite); data security protocols during production | Low residual with backup discipline
Risk Score = Probability × Impact (1-5). Red ≥ 2.0, Yellow 1.0-1.9, Green < 1.0. Provide this register in full investor due diligence package (not in first pitch). Revisit quarterly.